## Sheet1
Chace Studio |  | Just Dandy
| Asset Name | Notes (Asset Purpose) | Due Date | Status
Scripts/Mechs | Player Controller | Purpose is to be able to control the player | 2022-12-16 | Complete
| Crosshair (in player controller) | Purpose is to be able to aim easier | 2022-12-16 | Complete
| Grow System (in player controller) | Grow each stage by collecting pollen to become stronger | 2022-12-16 | Complete
| Enemy Controller | Purpose is to be able to fight enemies | 2022-12-16 | Complete
| Boss Controller (maybe) | Purpose is to be able to have different stages and attacks for the boss | 2022-12-16 | Cut
| Game Manager | Purpose is to select levels or control each level | 2022-12-16 | Complete
| Options Menu Manager (Optional) | Purpose is to be able to change settings | 2022-12-16 | Complete
| Environment Script | To control the environment and delete projectiles on impact | 2022-12-16 | Complete
Levels | Menu Screen | Purpose is to be able to change settings, start game, or quit | 2022-12-16 | Complete
| Tutorial/Level 1 (forest) | Purpose is to teach player how to play the game | 2022-12-16 | Complete
| Level 2 (mud) | Fight enemies | 2022-12-16 | Complete
| Level 3 (rocky) | Fight stronger enemies | 2022-12-16 | Complete
| Level 4 (garden) | Boss/Final level | 2022-12-16 | Cut
| Win Screen | Purpose is to show that the player won | 2022-12-16 | Complete
Music/SFX | Menu Music | music in the menu | 2022-12-16 | Complete
| Level 1 Music | music in level 1 | 2022-12-16 | Complete
| Level 2 Music | music in level 2 | 2022-12-16 | Incomplete
| Level 3 Music | music in level 3 | 2022-12-16 | Incomplete
| Level 4 Music | music in level 4 | 2022-12-16 | Cut
| Smack Sound Effect | to indicate when something is hit | 2022-12-16 | Complete
| Damage Sound | to alert when damage is taken | 2022-12-16 | Complete
| Death Sound | to indicate when something dies | 2022-12-16 | Complete
| Shoot Sound | to indicate shooting | 2022-12-16 | Complete
| Win Music | to indicate when you win | 2022-12-16 | Incomplete
| Enemy Sounds | to show when an enemy is near | 2022-12-16 | Complete
| Cutscene Sounds (Optional) | nice to have | 2022-12-16 | Cut
Art/Animation | Crosshair | to show where the player will attack | 2022-12-16 | Complete
| Player Stage 1 | to show that you are in the 1st stage | 2022-12-16 | Complete
| Player Stage 2 | to show that you are in the 2nd stage | 2022-12-16 | Incomplete
| Player Stage 3 | to show that you are in the 3rd stage | 2022-12-16 | Incomplete
| Player Stage 4 | to show that you are in the 4th stage | 2022-12-16 | Incomplete
| Aphid Enemy | to see the aphid enemy | 2022-12-16 | Incomplete
| Beetle Enemy | to see the beetle enemy | 2022-12-16 | Complete
| Slug Enemy | to see the slug enemy | 2022-12-16 | Complete
| Snail Enemy | to see the snail enemy | 2022-12-16 | Complete
| Hand Boss | to see the boss | 2022-12-16 | Cut
| Level 1 Background | to give a background on level 1 | 2022-12-16 | Complete
| Level 2 Background | to give a background on level 2 | 2022-12-16 | Incomplete
| Level 3 Background | to give a background on level 3 | 2022-12-16 | Incomplete
| Level 4 Background | to give a background on level 4 | 2022-12-16 | Cut
| Menu UI | to start/quit game | 2022-12-16 | Complete
| Health UI | to see your health | 2022-12-16 | Complete
| Win UI | to see when you when | 2022-12-16 | Complete
| Pollen Object | to be able to level up | 2022-12-16 | Complete
| Pause Menu | to pick what you want to do | 2022-12-16 | Complete
| Health Drop (Optional) | "Nice to Have" | 2022-12-16 | Cut
| Projectile | to see where you are shooting | 2022-12-16 | Incomplete